## Overview
Workplace Settings — QA final status
As at 30 Oct 2026 ¦ PR #595 ¦ pushed head 6be84e50c ¦ develop 20bc8d023
Coverage group | Specs | Unique settings | Scenarios | Recorded status
In PR #595 — in scope | 184 | 209 | 407 | Historical passes; in-scope coverage
Held settings | 3 | 2 + 1 shared PR setting | 7 | See coverage sheet; plus 1 held product check
Count reconciliation |  |  | 406 attributed in-scope scenarios plus one shared Explore baseline = 407 scenarios. Held work remains separate: 7 scenarios plus 1 product check.
Sum of in-scope PR row counts | 406
Shared Explore empty baseline | 1
Current-scope PR scenarios | 407
Attributed counts + shared baseline | 407
Jira | Latest develop status | Revision |  | Evidence / interpretation | Detail
PPT-2859 | Verified fixed | 20bc8d023 |  | PR full run | 29 Oct 2026: 422 tests; 417 passed; 5 failures.
PPT-2861 | Verified fixed | 20bc8d023 |  | Failure disposition | 4 held local failures; 1 events.room_as_host dev-server hiccup passed 6/6 on repeat.
PPT-2862 | Verified fixed | 20bc8d023 |  | Typecheck | No errors, as recorded in the report.
PPT-2863 | Verified fixed | 20bc8d023 |  | Local uncommitted change | bookings.allow-all-day uses tomorrow; assertions unchanged; 2/2 passed on PR app.
PPT-2858 | Verified fixed | 20bc8d023 |  | PASS | Documented behavior checked.
PPT-2864 | Verified fixed | 20bc8d023 |  | PASS (current behaviour) | Passing assertion of current buggy behavior; requires update after fixes reach the PR branch.
PPT-2865 | Verified fixed | 20bc8d023 |  | Value evidence | Statically read existing specs; no E2E test was executed to create this workbook. Values include relevant fixed controls in shared specs.
PPT-2866 | Verified fixed | 20bc8d023
PPT-2854 | Verified fixed | 20bc8d023
PPT-2860 | Open | 20bc8d023
PPT-2868 | Open | 20bc8d023
PPT-2869 | Open | 20bc8d023
PPT-2870 | Open | 20bc8d023
Spec updates after merge | Case | Jira
bookings.allow-all-day | true case | PPT-2859
parking-booking.allow-all-day | "false alone" case | PPT-2859
bookings.has-assets | true + desks false | PPT-2864
desk-booking.allow-time-changes | false case | PPT-2862
explore.map-overlays | explore.disable | PPT-2866 / PPT-2854
Source: /Users/sharmila/Downloads/user-interfaces-e2e-workplace-settings/local/audits/workplace-settings-final-status.md Report source contains a scope-cleaned version of the original status report. No tests were rerun while editing this workbook.

## Settings coverage
Settings coverage and verified value variations
In-scope coverage only. PR results remain historical; no tests rerun.
Only in-scope Settings coverage is listed below.
Area | Setting | Coverage scope | No. of tests | Values / combinations verified | Scenario variations / assertions | PR branch status | Develop status (20bc8d023) | Jira / follow-up | Existing spec | Notes / next step | Evidence
bookings | bookings.all_day_default | In PR #595 | 2 | false true | bookings.all_day_default false initializes the visitor timed or all-day form bookings.all_day_default true initializes the visitor timed or all-day form | PASS | Not specified in report |  | bookings.all-day-default |  | apps/workplace/e2e/settings/bookings/bookings.all-day-default.spec.ts; status MD line 36
bookings | bookings.allow_all_day | In PR #595 | 2 | false true | bookings.allow_all_day false supplies the generic desk all-day option bookings.allow_all_day true supplies the generic desk all-day option | PASS (current behaviour) | PPT-2859: Verified fixed | PPT-2859 | bookings.allow-all-day | PPT-2859 fixed on develop; the true case needs updating after the merge | apps/workplace/e2e/settings/bookings/bookings.allow-all-day.spec.ts; status MD line 37
bookings | bookings.bookable_hours | In PR #595 | 2 | null {"start":9,"end":17} | bookings.bookable_hours false restricts visitor start-time choices through the fallback bookings.bookable_hours true restricts visitor start-time choices through the fallback | PASS | Not specified in report |  | bookings.bookable-hours |  | apps/workplace/e2e/settings/bookings/bookings.bookable-hours.spec.ts; status MD line 38
bookings | bookings.can_book_for_anyone | In PR #595 | 2 | false true | bookings.can_book_for_anyone false supplies an unset visitor host-search preference bookings.can_book_for_anyone true supplies an unset visitor host-search preference | PASS | Not specified in report |  | bookings.can-book-for-anyone |  | apps/workplace/e2e/settings/bookings/bookings.can-book-for-anyone.spec.ts; status MD line 39
bookings | bookings.can_book_for_others | In PR #595 | 2 | false true | bookings.can_book_for_others false supplies an unset visitor delegation preference bookings.can_book_for_others true supplies an unset visitor delegation preference | PASS | Not specified in report |  | bookings.can-book-for-others |  | apps/workplace/e2e/settings/bookings/bookings.can-book-for-others.spec.ts; status MD line 40
bookings | bookings.custom_duration_options | In PR #595 | 2 | [] [45,150] | booking settings: bookings.custom_duration_options false supplies visitor duration exceptions booking settings: bookings.custom_duration_options true supplies visitor duration exceptions | PASS | Not specified in report |  | bookings.custom-duration-options |  | apps/workplace/e2e/settings/bookings/bookings.custom-duration-options.spec.ts; status MD line 41
bookings | bookings.min_duration | In PR #595 | 2 | 60 90 | booking settings: bookings.min_duration 60 bounds visitor fallback duration options booking settings: bookings.min_duration 90 bounds visitor fallback duration options | PASS | Not specified in report |  | bookings.duration-bounds |  | apps/workplace/e2e/settings/bookings/bookings.duration-bounds.spec.ts; status MD line 42
bookings | bookings.max_duration | In PR #595 | 2 | 120 150 | booking settings: bookings.max_duration 120 bounds visitor fallback duration options booking settings: bookings.max_duration 150 bounds visitor fallback duration options | PASS | Not specified in report |  | bookings.duration-bounds |  | apps/workplace/e2e/settings/bookings/bookings.duration-bounds.spec.ts; status MD line 43
bookings | bookings.duration_step | In PR #595 | 2 | 30 45 | booking settings: bookings.duration_step 30 controls visitor fallback duration increments booking settings: bookings.duration_step 45 controls visitor fallback duration increments | PASS | Not specified in report |  | bookings.duration-step |  | apps/workplace/e2e/settings/bookings/bookings.duration-step.spec.ts; status MD line 44
bookings | bookings.has_assets | In PR #595 | 2 | false true | bookings.has_assets false gates the desk asset request field with desks.has_assets false bookings.has_assets true gates the desk asset request field with desks.has_assets false | PASS (current behaviour) | PPT-2864: Verified fixed | PPT-2864 | bookings.has-assets | PPT-2864 fixed on develop; update after the merge | apps/workplace/e2e/settings/bookings/bookings.has-assets.spec.ts; status MD line 45
bookings | bookings.use_building_timezone | In PR #595 | 2 | false true | bookings.use_building_timezone false gates the visitor secondary timezone label bookings.use_building_timezone true gates the visitor secondary timezone label | PASS | Not specified in report |  | bookings.use-building-timezone | Also tested on the locker form (lockers area) | apps/workplace/e2e/settings/bookings/bookings.use-building-timezone.spec.ts; status MD line 46
chat | chat.enabled | In PR #595 | 2 | false true | chat.enabled false gates the chat launcher chat.enabled true gates the chat launcher | PASS | Not specified in report |  | chat.enabled |  | apps/workplace/e2e/settings/chat/chat.enabled.spec.ts; status MD line 51
desk-booking | desks.allow_all_day | In PR #595 | 2 | false true | desk settings: desks.allow_all_day false gates the all-day checkbox desk settings: desks.allow_all_day true gates the all-day checkbox | PASS | PPT-2859: Verified fixed | PPT-2859 | desk-booking.allow-all-day |  | apps/workplace/e2e/settings/desk-booking/desk-booking.allow-all-day.spec.ts; status MD line 56
desk-booking | desks.allow_groups | In PR #595 | 2 | false true | desk settings: desks.allow_groups false gates group mode and local member entry desk settings: desks.allow_groups true gates group mode and local member entry | PASS | Not specified in report |  | desk-booking.allow-groups |  | apps/workplace/e2e/settings/desk-booking/desk-booking.allow-groups.spec.ts; status MD line 57
desk-booking | desks.allow_multiple | In PR #595 | 2 | false true | desks.allow_multiple false accumulates or replaces local desk picks desks.allow_multiple true accumulates or replaces local desk picks | PASS | Not specified in report |  | desk-booking.allow-multiple |  | apps/workplace/e2e/settings/desk-booking/desk-booking.allow-multiple.spec.ts; status MD line 58
desk-booking | desks.allow_recurrence | In PR #595 | 2 | false true | desk settings: desks.allow_recurrence false gates the unsaved recurrence field desk settings: desks.allow_recurrence true gates the unsaved recurrence field | PASS | Not specified in report |  | desk-booking.allow-recurrence |  | apps/workplace/e2e/settings/desk-booking/desk-booking.allow-recurrence.spec.ts; status MD line 59
desk-booking | desks.allow_time_changes | In PR #595 | 1 | false | desk settings: desks.allow_time_changes false gates the all-day checkbox | PASS (current behaviour) | PPT-2862: Verified fixed | PPT-2862 | desk-booking.allow-time-changes | PPT-2862 fixed on develop; update after the merge | apps/workplace/e2e/settings/desk-booking/desk-booking.allow-time-changes.spec.ts; status MD line 60
desk-booking | bookings.allowed_daily_desk_count | In PR #595 | 2 | 1 2 | desk settings: bookings.allowed_daily_desk_count 1 refuses a second desk booking that day desk settings: bookings.allowed_daily_desk_count 2 allows a second desk booking that day | PASS | Not specified in report |  | desk-booking.allowed-daily-desk-count | Added in 6be84e50c | apps/workplace/e2e/settings/desk-booking/desk-booking.allowed-daily-desk-count.spec.ts; status MD line 61
desk-booking | bookings.assigned_resource_booking | In PR #595 | 2 | "deny" "allow" | desk settings: bookings.assigned_resource_booking deny controls the legacy assigned-desk overlay desk settings: bookings.assigned_resource_booking allow controls the legacy assigned-desk overlay | PASS | Not specified in report |  | desk-booking.assigned-resource-booking | Legacy desk flow | apps/workplace/e2e/settings/desk-booking/desk-booking.assigned-resource-booking.spec.ts; status MD line 62
desk-booking | desks.auto_allocation | In PR #595 | 2 | false true | desks.auto_allocation false switches automatic versus manual selection layout desks.auto_allocation true switches automatic versus manual selection layout | PASS | Not specified in report |  | desk-booking.auto-allocation |  | apps/workplace/e2e/settings/desk-booking/desk-booking.auto-allocation.spec.ts; status MD line 63
desk-booking | desks.auto_checkin | In PR #595 | 2 | false true | desks.auto_checkin false shows the booking check-in control desks.auto_checkin true hides the booking check-in control | PASS | Not specified in report |  | desk-booking.auto-checkin |  | apps/workplace/e2e/settings/desk-booking/desk-booking.auto-checkin.spec.ts; status MD line 64
desk-booking | desks.available_period | In PR #595 | 2 | 7 14 | desk settings: desks.available_period 7 gates the calendar horizon desk settings: desks.available_period 14 gates the calendar horizon | PASS | Not specified in report |  | desk-booking.available-period |  | apps/workplace/e2e/settings/desk-booking/desk-booking.available-period.spec.ts; status MD line 65
desk-booking | desks.bookable_hours | In PR #595 | 3 | null {"start":6,"end":11} {"start":9,"end":17} | desk settings: desks.bookable_hours unset bounds tomorrow time options desk settings: desks.bookable_hours 6-11 bounds tomorrow time options desk settings: desks.bookable_hours 9-17 bounds tomorrow time options | PASS | Not specified in report |  | desk-booking.bookable-hours |  | apps/workplace/e2e/settings/desk-booking/desk-booking.bookable-hours.spec.ts; status MD line 66
desk-booking | desks.can_book_for_others | In PR #595 | 2 | false true | desk settings: desks.can_book_for_others false gates delegate mode with an empty host selector desk settings: desks.can_book_for_others true gates delegate mode with an empty host selector | PASS | PPT-2869: Open | PPT-2869 | desk-booking.can-book-for-others | Open PPT-2869 concerns the explicit-false override, which this spec doesn't cover | apps/workplace/e2e/settings/desk-booking/desk-booking.can-book-for-others.spec.ts; status MD line 67
desk-booking | desks.can_book_lockers | In PR #595 | 2 | false true | desks.can_book_lockers false gates the local secondary locker option desks.can_book_lockers true gates the local secondary locker option | PASS | Not specified in report |  | desk-booking.can-book-lockers |  | apps/workplace/e2e/settings/desk-booking/desk-booking.can-book-lockers.spec.ts; status MD line 68
desk-booking | desks.custom_duration_options | In PR #595 | 2 | [] [45,150] | desk settings: desks.custom_duration_options false changes exact duration choices desk settings: desks.custom_duration_options true changes exact duration choices | PASS | Not specified in report |  | desk-booking.custom-duration-options |  | apps/workplace/e2e/settings/desk-booking/desk-booking.custom-duration-options.spec.ts; status MD line 69
desk-booking | desks.default_duration | In PR #595 | 2 | 90 150 | desks.default_duration 90 sets the new desk booking length desks.default_duration 150 sets the new desk booking length | PASS | Not specified in report |  | desk-booking.default-duration |  | apps/workplace/e2e/settings/desk-booking/desk-booking.default-duration.spec.ts; status MD line 70
desk-booking | desks.duration_step | In PR #595 | 1 | 45 (30-minute baseline control) | desk settings: desks.duration_step 45 changes exact duration choices | PASS | Not specified in report |  | desk-booking.duration-step |  | apps/workplace/e2e/settings/desk-booking/desk-booking.duration-step.spec.ts; status MD line 72
desk-booking | bookings.force_current_user_for_booking_rules | In PR #595 | 2 | false true | bookings.force_current_user_for_booking_rules false selects rules host groups bookings.force_current_user_for_booking_rules true selects rules host groups | PASS | Not specified in report |  | desk-booking.force-current-user-for-booking-rules |  | apps/workplace/e2e/settings/desk-booking/desk-booking.force-current-user-for-booking-rules.spec.ts; status MD line 73
desk-booking | desks.has_assets | In PR #595 | 2 | false true | desks.has_assets false gates the asset request field with generic flag false desks.has_assets true gates the asset request field with generic flag false | PASS | PPT-2864: Verified fixed | PPT-2864 | desk-booking.has-assets |  | apps/workplace/e2e/settings/desk-booking/desk-booking.has-assets.spec.ts; status MD line 74
desk-booking | desks.height_enabled | In PR #595 | 2 | false true | desks.height_enabled false does not add the desk-height control desks.height_enabled true adds the desk-height control and presets | PASS | Not specified in report |  | desk-booking.height-enabled |  | apps/workplace/e2e/settings/desk-booking/desk-booking.height-enabled.spec.ts; status MD line 75
desk-booking | bookings.hide_checkin | In PR #595 | 2 | false true | bookings.hide_checkin false gates the control on a synthetic owned desk booking bookings.hide_checkin true gates the control on a synthetic owned desk booking | PASS | Not specified in report |  | desk-booking.hide-checkin |  | apps/workplace/e2e/settings/desk-booking/desk-booking.hide-checkin.spec.ts; status MD line 76
desk-booking | desks.max_duration | In PR #595 | 1 | 180 | desk settings: desks.max_duration 180 changes exact duration choices | PASS | Not specified in report |  | desk-booking.max-duration |  | apps/workplace/e2e/settings/desk-booking/desk-booking.max-duration.spec.ts; status MD line 77
desk-booking | desks.min_duration | In PR #595 | 1 | 30 | desk settings: desks.min_duration 30 changes exact duration choices | PASS | Not specified in report |  | desk-booking.min-duration |  | apps/workplace/e2e/settings/desk-booking/desk-booking.min-duration.spec.ts; status MD line 78
desk-booking | desks.show_calendar_links | In PR #595 | 2 | false true | desks.show_calendar_links false gates links for browser-only success state desks.show_calendar_links true gates links for browser-only success state | PASS | Not specified in report |  | desk-booking.show-calendar-links |  | apps/workplace/e2e/settings/desk-booking/desk-booking.show-calendar-links.spec.ts; status MD line 79
desk-booking | desks.show_users | In PR #595 | 3 | false true null | desks.show_users false gates desk booking user data on the map desks.show_users true gates desk booking user data on the map desks.show_users null gates desk booking user data on the map | PASS | Not specified in report |  | desk-booking.show-users |  | apps/workplace/e2e/settings/desk-booking/desk-booking.show-users.spec.ts; status MD line 80
desk-booking | desks.use_assets | In PR #595 | 2 | false true | desks.use_assets false selects assets API versus level metadata desks.use_assets true selects assets API versus level metadata | PASS | Not specified in report |  | desk-booking.use-assets |  | apps/workplace/e2e/settings/desk-booking/desk-booking.use-assets.spec.ts; status MD line 81
desk-booking | desks.use_building_timezone | In PR #595 | 2 | false true | desks.use_building_timezone false gates the duration secondary time line desks.use_building_timezone true gates the duration secondary time line | PASS | Not specified in report |  | desk-booking.use-building-timezone |  | apps/workplace/e2e/settings/desk-booking/desk-booking.use-building-timezone.spec.ts; status MD line 82
directory | users.min_search_length | In PR #595 | 2 | 14 15 | users.min_search_length 14 gates directory lookup at its boundary users.min_search_length 15 gates directory lookup at its boundary | PASS | Not specified in report |  | directory.min-search-length |  | apps/workplace/e2e/settings/directory/directory.min-search-length.spec.ts; status MD line 87
directory | users.show_avatars | In PR #595 | 2 | false true | users.show_avatars false changes directory results without losing identity users.show_avatars true changes directory results without losing identity | PASS | Not specified in report |  | directory.show-avatars |  | apps/workplace/e2e/settings/directory/directory.show-avatars.spec.ts; status MD line 88
explore | explore.colors | In PR #595 | 2 | {"space-free":"#123456"} {"free":"#654321"} | explore.colors space-free paints the free desk #123456 explore.colors free paints the free desk #654321 | PASS | Not specified in report |  | explore.colors |  | apps/workplace/e2e/settings/explore/explore.colors.spec.ts; status MD line 93
explore | explore.legend | In PR #595 | 2 | [] Four pairs: Free #123456; Busy #654321; Pending #112233; Closed #445566 | explore.legend of four pairs collapses behind a toggle explore.legend empty renders no legend even when shown | PASS | Not specified in report |  | explore.legend |  | apps/workplace/e2e/settings/explore/explore.legend.spec.ts; status MD line 94
explore | explore.hide_zones | In PR #595 | 2 | false true | explore.hide_zones false shows the Areas overlay toggle explore.hide_zones true removes the Areas overlay toggle | PASS | Not specified in report |  | explore.map-overlays |  | apps/workplace/e2e/settings/explore/explore.map-overlays.spec.ts; status MD line 95
explore | explore.hide_devices | In PR #595 | 2 | true false | explore.hide_devices false shows the Show Devices overlay toggle explore.hide_devices true removes the Show Devices overlay toggle | PASS | Not specified in report |  | explore.map-overlays |  | apps/workplace/e2e/settings/explore/explore.map-overlays.spec.ts; status MD line 96
explore | explore.hide_sensors | In PR #595 | 2 | true false | explore.hide_sensors false shows the Show Sensors overlay toggle explore.hide_sensors true removes the Show Sensors overlay toggle | PASS | Not specified in report |  | explore.map-overlays |  | apps/workplace/e2e/settings/explore/explore.map-overlays.spec.ts; status MD line 97
explore | explore.disable | In PR #595 | 2 | [] ["devices"] | explore.disable devices keeps the Show Devices toggle off after a click explore.disable without devices allows the Show Devices toggle to turn on | PASS (current behaviour) | PPT-2866: Verified fixed PPT-2854: Verified fixed | PPT-2866 / PPT-2854 | explore.map-overlays | PPT-2866 / PPT-2854 fixed on develop (switch now hidden); update after the merge. Was intermittent before. | apps/workplace/e2e/settings/explore/explore.map-overlays.spec.ts; status MD line 98
explore | explore.show_legend | In PR #595 | 2 | false true | explore.show_legend false hides a configured legend explore.show_legend true with explore.legend of two pairs renders labels and colours | PASS | Not specified in report |  | explore.show-legend |  | apps/workplace/e2e/settings/explore/explore.show-legend.spec.ts; status MD line 99
explore | explore.area_count_key | In PR #595 | 2 | "count" "people_count" | explore.area_count_key=count paints the selected occupancy status explore.area_count_key=people_count paints the selected occupancy status | PASS | Not specified in report |  | explore.area-count-key |  | apps/workplace/e2e/settings/explore/explore.area-count-key.spec.ts; status MD line 100
explore | explore.show_booking_qr | In PR #595 | 2 | true false | explore.show_booking_qr=true opens only the selected room dialog explore.show_booking_qr=false opens only the selected room dialog | PASS | Not specified in report |  | explore.show-booking-qr |  | apps/workplace/e2e/settings/explore/explore.show-booking-qr.spec.ts; status MD line 101
explore | explore.show_event_details | In PR #595 | 2 | true false | explore.show_event_details=true controls details in the live room tooltip explore.show_event_details=false controls details in the live room tooltip | PASS | Not specified in report |  | explore.show-event-details |  | apps/workplace/e2e/settings/explore/explore.show-event-details.spec.ts; status MD line 102
explore | show_presence_indicators | In PR #595 | 2 | true false | show_presence_indicators true sets the room presence icon on the Explore map show_presence_indicators false sets the room presence icon on the Explore map | PASS | Not specified in report |  | explore.show-presence-indicators |  | apps/workplace/e2e/settings/explore/explore.show-presence-indicators.spec.ts; status MD line 103
explore | explore.show_zone_sensor_info | In PR #595 | 2 | true false | explore.show_zone_sensor_info=true controls the room sensor tooltip explore.show_zone_sensor_info=false controls the room sensor tooltip | PASS | Not specified in report |  | explore.show-zone-sensor-info |  | apps/workplace/e2e/settings/explore/explore.show-zone-sensor-info.spec.ts; status MD line 104
explore | explore.use_zone_polygons | In PR #595 | 2 | true false | explore.use_zone_polygons=true renders the area using the selected drawing path explore.use_zone_polygons=false renders the area using the selected drawing path | PASS | Not specified in report |  | explore.zone-polygons-and-labels |  | apps/workplace/e2e/settings/explore/explore.zone-polygons-and-labels.spec.ts; status MD line 106
explore | explore.show_zone_labels | In PR #595 | 2 | true false | explore.show_zone_labels=true controls the rendered sensor label explore.show_zone_labels=false controls the rendered sensor label | PASS | Not specified in report |  | explore.zone-polygons-and-labels |  | apps/workplace/e2e/settings/explore/explore.zone-polygons-and-labels.spec.ts; status MD line 107
explore | explore.disable_labels | In PR #595 | 2 | [] ["zones"] | explore.disable_labels=[] filters zone labels while retaining the area explore.disable_labels=[zones] filters zone labels while retaining the area | PASS | Not specified in report |  | explore.zone-polygons-and-labels |  | apps/workplace/e2e/settings/explore/explore.zone-polygons-and-labels.spec.ts; status MD line 108
explore | explore.disable_features | In PR #595 | 3 | [] ["desks"] "desks" ["zones"] | explore.disable_features ['desks'] filters the Explore map groups explore.disable_features 'desks' (comma string) filters the Explore map groups explore.disable_features ['zones'] filters the Explore map groups | PASS | Not specified in report |  | explore.disable-layers | Includes the comma-string form | apps/workplace/e2e/settings/explore/explore.disable-layers.spec.ts; status MD line 109
explore | explore.disable_actions | In PR #595 | 1 | [] ["desks"] | explore.disable_actions ['desks'] filters the Explore map groups | PASS | Not specified in report |  | explore.disable-layers |  | apps/workplace/e2e/settings/explore/explore.disable-layers.spec.ts; status MD line 110
explore | explore.disable_styles | In PR #595 | 1 | [] ["desks"] | explore.disable_styles ['desks'] filters the Explore map groups | PASS | Not specified in report |  | explore.disable-layers | The spec also has 1 shared baseline scenario (all empty), giving 6 in total | apps/workplace/e2e/settings/explore/explore.disable-layers.spec.ts; status MD line 111
explore | desks.enable_maps | In PR #595 | 2 | false true | desks.enable_maps false publishes 0 desk map actions desks.enable_maps true publishes 4 desk map actions | PASS | Not specified in report |  | explore.enable-maps |  | apps/workplace/e2e/settings/explore/explore.enable-maps.spec.ts; status MD line 112
explore | parking.enable_maps | In PR #595 | 2 | false true | parking.enable_maps false publishes 0 parking map actions parking.enable_maps true publishes 1 parking map actions | PASS | Not specified in report |  | explore.enable-maps |  | apps/workplace/e2e/settings/explore/explore.enable-maps.spec.ts; status MD line 113
general | allow_dark_mode | In PR #595 | 2 | false true | allow_dark_mode false gates a saved dark theme allow_dark_mode true gates a saved dark theme | PASS | Not specified in report |  | general.allow-dark-mode |  | apps/workplace/e2e/settings/general/general.allow-dark-mode.spec.ts; status MD line 118
general | banner.type, banner.content, banner.id | In PR #595 | 5 | banner.id = "prepared-banner-warn" banner.type = "warn" banner.content = "Prepared banner warn" banner.id = "prepared-banner-error" banner.type = "error" banner.content = "Prepared banner error" banner.id = "prepared-banner-empty" banner.type = "info" banner.content = "" banner.id = "prepared-banner-dismiss" banner.content = "Prepared dismissible banner" banner.id = "prepared-banner-new" banner.content = "Prepared new banner" | banner type warn renders the configured content and colour banner type error renders the configured content and colour banner with empty content stays hidden after setup banner close remembers banner.id in browser storage only banner with a new id shows again after an earlier banner was dismissed | PASS | Not specified in report |  | general.banner | 3 Settings | apps/workplace/e2e/settings/general/general.banner.spec.ts; status MD line 119
general | basic_user_search | In PR #595 | 1 | true | general settings: basic_user_search true selects the landing colleague search source | PASS | Not specified in report |  | general.basic-user-search |  | apps/workplace/e2e/settings/general/general.basic-user-search.spec.ts; status MD line 120
general | css_variables_dark | In PR #595 | 2 | {"secondary":"#123456"} {} | css_variables_dark emits a dark-theme rule and the property resolves css_variables_dark {} leaves the dark-theme rule empty | PASS | Not specified in report |  | general.css-variables-dark |  | apps/workplace/e2e/settings/general/general.css-variables-dark.spec.ts; status MD line 121
general | css_variables | In PR #595 | 2 | {"brand-500":"#123456","base-100":"#234567"} {} | css_variables supplies multiple computed theme values in an isolated page css_variables empty map replaces the configured override map without leaking contexts | PASS | Not specified in report |  | general.css-variables |  | apps/workplace/e2e/settings/general/general.css-variables.spec.ts; status MD line 122
general | currency | In PR #595 | 2 | "EUR" "GBP" | currency EUR formats browser-only native catering prices currency GBP formats browser-only native catering prices | PASS | Not specified in report |  | general.currency |  | apps/workplace/e2e/settings/general/general.currency.spec.ts; status MD line 123
general | default_building | In PR #595 | 2 | "e2e-default-building-b" "e2e-default-building-a" | default_building selects building B when the user has no saved building default_building selects building A when the user has no saved building | PASS | Not specified in report |  | general.default-building |  | apps/workplace/e2e/settings/general/general.default-building.spec.ts; status MD line 124
general | default_route | In PR #595 | 1 | "/directory" | default_route redirects the application entry route to the configured route | PASS | Not specified in report |  | general.default-route |  | apps/workplace/e2e/settings/general/general.default-route.spec.ts; status MD line 125
general | environment_bar | In PR #595 | 1 | "#123456" "" | environment_bar renders the configured colour and clears for an empty value | PASS | Not specified in report |  | general.environment-bar |  | apps/workplace/e2e/settings/general/general.environment-bar.spec.ts; status MD line 126
general | features | In PR #595 | 2 | ["desks"] ["spaces"] [] | features replacement exposes only each configured booking destination features empty list removes the quick-actions booking widget | PASS | Not specified in report |  | general.features |  | apps/workplace/e2e/settings/general/general.features.spec.ts; status MD line 127
general | global_search | In PR #595 | 1 | true false | global_search shows and hides the topbar search control | PASS | Not specified in report |  | general.global-search |  | apps/workplace/e2e/settings/general/general.global-search.spec.ts; status MD line 128
general | group_events_calendar | In PR #595 | 2 | "settings-calendar-a@example.invalid" "settings-calendar-b@example.invalid" | group_events_calendar settings-calendar-a@example.invalid scopes the calendar lookup group_events_calendar settings-calendar-b@example.invalid scopes the calendar lookup | PASS | Not specified in report |  | general.group-events-calendar |  | apps/workplace/e2e/settings/general/general.group-events-calendar.spec.ts; status MD line 129
general | help | In PR #595 | 2 | [{"name":"E2E Workplace Help","link":"https://example.invalid/e2e-workplace-help","icon":{"type":"icon","class":"material-symbols-rounded","content":"help"}}] [] | help renders a configured tile link help [] leaves the help tooltip without link tiles | PASS | Not specified in report |  | general.help-menu |  | apps/workplace/e2e/settings/general/general.help-menu.spec.ts; status MD line 130
general | hide_global_search_items | In PR #595 | 3 | [] ["users"] ["spaces"] | hide_global_search_items [] shows the matching user and space hide_global_search_items [users] hides the user but not the space hide_global_search_items [spaces] hides the space but not the user | PASS | Not specified in report |  | general.hide-global-search-items |  | apps/workplace/e2e/settings/general/general.hide-global-search-items.spec.ts; status MD line 131
general | locales | In PR #595 | 2 | [{"id":"en-AU","name":"E2E English","local":"E2E English","flag":""},{"id":"fr","name":"E2E French","local":"E2E French","flag":""}] [] [{"id":"en-AU","name":"E2E English","local":"E2E English","flag":""}] | locales replaces language choices without persisting a language selection locales with zero or one entry hides the language selector while user controls remain | PASS | Not specified in report |  | general.locales |  | apps/workplace/e2e/settings/general/general.locales.spec.ts; status MD line 133
general | logo_dark | In PR #595 | 2 | SVG image data URL (navy) {src: SVG image data URL (purple)} | logo_dark string renders the configured image in dark mode logo_dark object renders the configured image in dark mode | PASS | Not specified in report |  | general.logo-dark |  | apps/workplace/e2e/settings/general/general.logo-dark.spec.ts; status MD line 134
general | logo_light | In PR #595 | 1 | SVG image data URL {src: SVG image data URL} | logo_light loads both string and object image configurations | PASS | Not specified in report |  | general.logo-light |  | apps/workplace/e2e/settings/general/general.logo-light.spec.ts; status MD line 135
general | menu_embeds | In PR #595 | 2 | [{"id":"e2e-local-guide","name":"E2E Local Guide","url":"https://example.invalid/guide","external":false,"icon":"help"}] [] [{"id":"e2e-external-guide","name":"E2E External Guide","url":"https://example.invalid/external","external":true}] | menu_embeds internal items point at the local embedded route and empty list removes them menu_embeds external items expose a safe new-tab link without navigation | PASS | Not specified in report |  | general.menu-embeds |  | apps/workplace/e2e/settings/general/general.menu-embeds.spec.ts; status MD line 136
general | name | In PR #595 | 1 | "E2E Workplace Name" | name supplies the browser title when short_name is empty | PASS | Not specified in report |  | general.name |  | apps/workplace/e2e/settings/general/general.name.spec.ts; status MD line 137
general | short_name | In PR #595 | 1 | "E2E Short" | short_name takes precedence over the full name in the browser title | PASS | Not specified in report |  | general.short-name |  | apps/workplace/e2e/settings/general/general.short-name.spec.ts; status MD line 138
general | show_changelog | In PR #595 | 1 | true false | show_changelog changes the version control between a button and plain text | PASS | Not specified in report |  | general.show-changelog |  | apps/workplace/e2e/settings/general/general.show-changelog.spec.ts; status MD line 139
general | support_issue_types | In PR #595 | 2 | ["E2E Issue Alpha","E2E Issue Beta"] [] | support_issue_types lists each configured issue type in the support form support_issue_types [] omits the issue type select | PASS | Not specified in report |  | general.support-ticket |  | apps/workplace/e2e/settings/general/general.support-ticket.spec.ts; status MD line 140
general | external_support_url | In PR #595 | 1 | Configured same-origin /e2e-external-support URL (form bypass) | external_support_url opens the configured URL instead of the support form | PASS | Not specified in report |  | general.support-ticket |  | apps/workplace/e2e/settings/general/general.support-ticket.spec.ts; status MD line 141
general | use_24_hour_time | In PR #595 | 2 | false true | general settings: use_24_hour_time false formats the 13:00 option and selected value general settings: use_24_hour_time true formats the 13:00 option and selected value | PASS | Not specified in report |  | general.use-24-hour-time |  | apps/workplace/e2e/settings/general/general.use-24-hour-time.spec.ts; status MD line 142
general | use_geolocation | In PR #595 | 3 | false true | use_geolocation false falls back without geolocation use_geolocation true at (40,40) chooses the nearest building B use_geolocation true at (10,10) chooses the nearest building A | PASS | Not specified in report |  | general.use-geolocation |  | apps/workplace/e2e/settings/general/general.use-geolocation.spec.ts; status MD line 143
general | use_region | In PR #595 | 2 | false true | use_region false scopes inline desk levels to region versus building use_region true scopes inline desk levels to region versus building | PASS | Not specified in report |  | general.use-region |  | apps/workplace/e2e/settings/general/general.use-region.spec.ts; status MD line 144
general | virtual_concierge.url | In PR #595 | 2 | "" "data:text/html;charset=utf-8,%3Ctitle%3EE2E%20Virtual%20Concierge%3C/title%3E" | virtual_concierge.url empty hides the concierge button virtual_concierge.url configured shows the concierge button virtual_concierge_url (legacy) is used when virtual_concierge.url is empty | PASS | Not specified in report |  | general.virtual-concierge |  | apps/workplace/e2e/settings/general/general.virtual-concierge.spec.ts; status MD line 145
general | virtual_concierge_url (legacy key) | In PR #595 | 1 | "" "data:text/html;charset=utf-8,%3Ctitle%3EE2E%20Virtual%20Concierge%3C/title%3E" | virtual_concierge_url (legacy) is used when virtual_concierge.url is empty | PASS | Not specified in report |  | general.virtual-concierge |  | apps/workplace/e2e/settings/general/general.virtual-concierge.spec.ts; status MD line 146
general | virtual_concierge.icon | In PR #595 | 2 | "" "data:image/svg+xml,%3Csvg%20xmlns%3D%22http%3A%2F%2Fwww.w3.org%2F2000%2Fsvg%22%20width%3D%2216%22%20height%3D%2216%22%3E%3Crect%20width%3D%2216%22%20height%3D%2216%22%20fill%3D%22%23123456%22%2F%3E%3C%2Fsvg%3E" | virtual_concierge.icon replaces the default support icon virtual_concierge.icon empty shows the default support icon | PASS | Not specified in report |  | general.virtual-concierge |  | apps/workplace/e2e/settings/general/general.virtual-concierge.spec.ts; status MD line 147
general | virtual_concierge.display | In PR #595 | 2 | "fullscreen" "sidebar" | virtual_concierge.display fullscreen opens the fullscreen embed virtual_concierge.display sidebar opens the sidebar embed | PASS | Not specified in report |  | general.virtual-concierge |  | apps/workplace/e2e/settings/general/general.virtual-concierge.spec.ts; status MD line 148
general | virtual_concierge.side | In PR #595 | 2 | "left" "right" | virtual_concierge.side right uses the right sidebar position virtual_concierge.side left uses the left sidebar position | PASS | Not specified in report |  | general.virtual-concierge |  | apps/workplace/e2e/settings/general/general.virtual-concierge.spec.ts; status MD line 149
general | week_start | In PR #595 | 2 | 0 1 | general settings: week_start 0 reorders current room-calendar weekdays general settings: week_start 1 reorders current room-calendar weekdays | PASS | Not specified in report |  | general.week-start |  | apps/workplace/e2e/settings/general/general.week-start.spec.ts; status MD line 150
landing | colleagues_require_auth | In PR #595 | 2 | true false | colleagues_require_auth true selects the landing colleague search source colleagues_require_auth false selects the landing colleague search source | PASS | Not specified in report |  | landing.colleagues-require-auth |  | apps/workplace/e2e/settings/landing/landing.colleagues-require-auth.spec.ts; status MD line 155
landing | feature_groups | In PR #595 | 3 | {} {"desks":["e2e-feature-group-that-no-staff-user-has"]} {"desks":["e2e-feature-group-member"]} | feature_groups without a restriction keeps the feature Quick Actions card feature_groups limiting desks to another group removes the Quick Actions card feature_groups limiting desks to a group the user is in keeps the Quick Actions card | PASS | Not specified in report |  | landing.feature-groups |  | apps/workplace/e2e/settings/landing/landing.feature-groups.spec.ts; status MD line 156
landing | hide_colleagues | In PR #595 | 1 | false true | hide_colleagues removes the colleagues panel and retains favourites | PASS | Not specified in report |  | landing.hide-colleagues |  | apps/workplace/e2e/settings/landing/landing.hide-colleagues.spec.ts; status MD line 157
landing | hide_landing_customise | In PR #595 | 2 | false true | hide_landing_customise false shows the Edit home screen control hide_landing_customise true removes the Edit home screen control and ignores a saved layout | PASS | Not specified in report |  | landing.hide-landing-customise |  | apps/workplace/e2e/settings/landing/landing.hide-landing-customise.spec.ts; status MD line 158
landing | hide_landing_rooms | In PR #595 | 1 | false true | hide_landing_rooms hides the room heading while levels remain | PASS | Not specified in report |  | landing.hide-landing-rooms |  | apps/workplace/e2e/settings/landing/landing.hide-landing-rooms.spec.ts; status MD line 159
landing | hide_landing_spaces | In PR #595 | 1 | false true | hide_landing_spaces hides the level heading while rooms remain | PASS | Not specified in report |  | landing.hide-landing-spaces |  | apps/workplace/e2e/settings/landing/landing.hide-landing-spaces.spec.ts; status MD line 161
landing | hide_landing_widgets | In PR #595 | 2 | [] ["favourites"] | hide_landing_widgets [] renders the default widgets hide_landing_widgets removes exactly the configured cards and cannot be added | PASS | Not specified in report |  | landing.hide-landing-widgets |  | apps/workplace/e2e/settings/landing/landing.hide-landing-widgets.spec.ts; status MD line 162
landing | show_quick_book | In PR #595 | 1 | true false | show_quick_book toggles booking actions without starting a booking | PASS | Not specified in report |  | landing.show-quick-book |  | apps/workplace/e2e/settings/landing/landing.show-quick-book.spec.ts; status MD line 163
landing | show_quick_links | In PR #595 | 1 | true false | show_quick_links toggles landing links while retaining the main content | PASS | Not specified in report |  | landing.show-quick-links |  | apps/workplace/e2e/settings/landing/landing.show-quick-links.spec.ts; status MD line 164
lockers | lockers.allow_all_day | In PR #595 | 2 | true false | lockers.allow_all_day true shows All day, which hides the time fields lockers.allow_all_day false removes the All day checkbox | PASS | Not specified in report |  | lockers.allow-all-day |  | apps/workplace/e2e/settings/lockers/lockers.allow-all-day.spec.ts; status MD line 169
lockers | lockers.allow_time_changes | In PR #595 | 2 | true false | lockers.allow_time_changes true gates the All day option lockers.allow_time_changes false gates the All day option | PASS | Not specified in report |  | lockers.allow-time-changes |  | apps/workplace/e2e/settings/lockers/lockers.allow-time-changes.spec.ts; status MD line 170
lockers | bookings.allowed_daily_locker_count | In PR #595 | 2 | 1 2 | locker settings: bookings.allowed_daily_locker_count 1 refuses a second locker booking that day locker settings: bookings.allowed_daily_locker_count 2 allows a second locker booking that day | PASS | Not specified in report |  | lockers.allowed-daily-locker-count | Added in 6be84e50c | apps/workplace/e2e/settings/lockers/lockers.allowed-daily-locker-count.spec.ts; status MD line 171
lockers | lockers.available_period | In PR #595 | 2 | 2 10 | lockers.available_period 2 disables days past the configured window lockers.available_period 10 allows the tenth day and disables the eleventh | PASS | Not specified in report |  | lockers.available-period |  | apps/workplace/e2e/settings/lockers/lockers.available-period.spec.ts; status MD line 172
lockers | lockers.disabled_date_select | In PR #595 | 2 | true false | lockers.disabled_date_select true controls the All day option beside the date lockers.disabled_date_select false controls the All day option beside the date | PASS (current behaviour) | PPT-2860: Open | PPT-2860 | lockers.disabled-date-select | PPT-2860 open: the fix isn't on develop. The date can still be changed. | apps/workplace/e2e/settings/lockers/lockers.disabled-date-select.spec.ts; status MD line 173
lockers | lockers.disabled_start_time | In PR #595 | 2 | true false | lockers.disabled_start_time true locks the start time lockers.disabled_start_time false locks the start time | PASS | Not specified in report |  | lockers.disabled-start-time |  | apps/workplace/e2e/settings/lockers/lockers.disabled-start-time.spec.ts; status MD line 174
lockers | lockers.hide_end_time | In PR #595 | 2 | true false | lockers.hide_end_time true controls the end-time field lockers.hide_end_time false controls the end-time field | PASS | Not specified in report |  | lockers.hide-end-time |  | apps/workplace/e2e/settings/lockers/lockers.hide-end-time.spec.ts; status MD line 175
lockers | lockers.hide_user | In PR #595 | 2 | false true | lockers.hide_user false sets the locker map user tooltips lockers.hide_user true sets the locker map user tooltips | PASS | PPT-2870: Open | PPT-2870 | lockers.hide-user | Added in 6be84e50c. Related open bug PPT-2870 (picker TypeError); the test avoids it. | apps/workplace/e2e/settings/lockers/lockers.hide-user.spec.ts; status MD line 176
lockers | lockers.max_duration | In PR #595 | 2 | 120 240 | lockers.max_duration 120 caps the hourly duration choices lockers.max_duration 240 caps the hourly duration choices | PASS | Not specified in report |  | lockers.max-duration |  | apps/workplace/e2e/settings/lockers/lockers.max-duration.spec.ts; status MD line 177
lockers | lockers.show_calendar_links | In PR #595 | 2 | true false | lockers.show_calendar_links true on the locker success page lockers.show_calendar_links false on the locker success page | PASS | Not specified in report |  | lockers.show-calendar-links |  | apps/workplace/e2e/settings/lockers/lockers.show-calendar-links.spec.ts; status MD line 178
lockers | bookings.use_building_timezone (locker form) | In PR #595 | 2 | true false | bookings.use_building_timezone true gates the locker building-time label bookings.use_building_timezone false gates the locker building-time label | PASS | Not specified in report |  | lockers.use-building-timezone | Same Setting as in bookings, so not counted again | apps/workplace/e2e/settings/lockers/lockers.use-building-timezone.spec.ts; status MD line 179
parking-booking | parking.allow_all_day | In PR #595 | 3 | true false | parking.allow_all_day true shows the All day checkbox, which hides the time fields parking.allow_all_day false (bookings false) removes the All day checkbox parking.allow_all_day false alone keeps the checkbox while bookings.allow_all_day is unset | PASS (current behaviour) | PPT-2859: Verified fixed | PPT-2859 | parking-booking.allow-all-day | PPT-2859 fixed on develop; the "false alone" case needs updating after the merge | apps/workplace/e2e/settings/parking-booking/parking-booking.allow-all-day.spec.ts; status MD line 184
parking-booking | bookings.allowed_daily_parking_count | In PR #595 | 2 | 1 2 | parking settings: bookings.allowed_daily_parking_count 1 refuses a second parking booking that day parking settings: bookings.allowed_daily_parking_count 2 allows a second parking booking that day | PASS | Not specified in report |  | parking-booking.allowed-daily-parking-count | Added in 6be84e50c | apps/workplace/e2e/settings/parking-booking/parking-booking.allowed-daily-parking-count.spec.ts; status MD line 185
parking-booking | parking.available_period | In PR #595 | 2 | 7 21 | parking.available_period 7 allows today+7 and blocks today+8 parking.available_period 21 extends the window to today+21 | PASS | Not specified in report |  | parking-booking.available-period |  | apps/workplace/e2e/settings/parking-booking/parking-booking.available-period.spec.ts; status MD line 186
parking-booking | parking.bookable_hours | In PR #595 | 3 | {"start":9,"end":17} {"start":6,"end":11} null | parking.bookable_hours 9-17 bounds tomorrow's start times parking.bookable_hours 6-11 bounds tomorrow's start times parking.bookable_hours unset offers the whole of tomorrow | PASS | Not specified in report |  | parking-booking.bookable-hours |  | apps/workplace/e2e/settings/parking-booking/parking-booking.bookable-hours.spec.ts; status MD line 187
parking-booking | parking.can_book_for_others | In PR #595 | 2 | true false | parking.can_book_for_others true controls the host selector parking.can_book_for_others false controls the host selector | PASS | PPT-2869: Open | PPT-2869 | parking-booking.can-book-for-others | Open PPT-2869 concerns the explicit-false override, which this spec doesn't cover | apps/workplace/e2e/settings/parking-booking/parking-booking.can-book-for-others.spec.ts; status MD line 188
parking-booking | parking.custom_duration_options | In PR #595 | 2 | [20,600] [] | parking.custom_duration_options adds out-of-step durations parking.custom_duration_options empty keeps the stepped 30-480 list | PASS | Not specified in report |  | parking-booking.custom-duration-options |  | apps/workplace/e2e/settings/parking-booking/parking-booking.custom-duration-options.spec.ts; status MD line 189
parking-booking | parking.hide_user (+ legacy parkings.hide_user) | In PR #595 | 3 | false true | parking.hide_user false renders a map feature for each parking space parking.hide_user true renders no map features while the list still works parking.hide_user legacy key app.parkings.hide_user still suppresses features | PASS | Not specified in report |  | parking-booking.hide-user |  | apps/workplace/e2e/settings/parking-booking/parking-booking.hide-user.spec.ts; status MD line 190
parking-booking | parking.max_duration | In PR #595 | 2 | 120 480 | parking.max_duration 120 caps the duration choices parking.max_duration 480 caps the duration choices | PASS | Not specified in report |  | parking-booking.max-duration |  | apps/workplace/e2e/settings/parking-booking/parking-booking.max-duration.spec.ts; status MD line 191
parking-booking | parking.min_duration | In PR #595 | 2 | 30 120 | parking.min_duration 30 moves the latest start within 9-17 hours parking.min_duration 120 moves the latest start within 9-17 hours | PASS | Not specified in report |  | parking-booking.min-duration |  | apps/workplace/e2e/settings/parking-booking/parking-booking.min-duration.spec.ts; status MD line 192
parking-booking | parking.restrict_home_location | In PR #595 | 3 | true false | parking.restrict_home_location true restricts parking at the assigned building parking.restrict_home_location false keeps the form at the assigned building parking.restrict_home_location true away from the assigned building keeps the form | PASS | Not specified in report |  | parking-booking.restrict-home-location |  | apps/workplace/e2e/settings/parking-booking/parking-booking.restrict-home-location.spec.ts; status MD line 193
parking-booking | parking.show_calendar_links | In PR #595 | 2 | false true | parking.show_calendar_links false gates the parking success links parking.show_calendar_links true gates the parking success links | PASS | Not specified in report |  | parking-booking.show-calendar-links |  | apps/workplace/e2e/settings/parking-booking/parking-booking.show-calendar-links.spec.ts; status MD line 194
parking-booking | parking.show_waitlist | In PR #595 | 2 | true false | parking.show_waitlist true colours a wait-listed request parking.show_waitlist false colours a wait-listed request | PASS | Not specified in report |  | parking-booking.show-waitlist |  | apps/workplace/e2e/settings/parking-booking/parking-booking.show-waitlist.spec.ts; status MD line 195
parking-booking | parking.use_building_timezone | In PR #595 | 2 | true false | parking.use_building_timezone true gates the building-time label parking.use_building_timezone false gates the building-time label | PASS | Not specified in report |  | parking-booking.use-building-timezone |  | apps/workplace/e2e/settings/parking-booking/parking-booking.use-building-timezone.spec.ts; status MD line 196
parking-booking | parking.show_status_details | In PR #595 | 2 | true false | parking.show_status_details true with show_users false sets the Explore parking hover card contents parking.show_status_details false sets the Explore parking hover card contents | PASS | Not specified in report |  | parking-booking.map-tooltip |  | apps/workplace/e2e/settings/parking-booking/parking-booking.map-tooltip.spec.ts; status MD line 197
parking-booking | parking.show_users | In PR #595 | 1 | false true | parking.show_users true sets the Explore parking hover card contents | PASS | Not specified in report |  | parking-booking.map-tooltip |  | apps/workplace/e2e/settings/parking-booking/parking-booking.map-tooltip.spec.ts; status MD line 198
parking-booking | parking.waitlist_week_start | In PR #595 | 2 | {day: current UTC weekday, hour:0, minute:0} {day: current UTC weekday, hour:0, minute:1} | parking.waitlist_week_start 00:00 renders Waitlisted parking.waitlist_week_start 00:01 renders Tentative | PASS | Not specified in report |  | parking-booking.waitlist-week-start |  | apps/workplace/e2e/settings/parking-booking/parking-booking.waitlist-week-start.spec.ts; status MD line 199
parking-request | parking.allow_recurrence | In PR #595 | 2 | true false | parking.allow_recurrence true controls the Single Day / Multi-day choice parking.allow_recurrence false controls the Single Day / Multi-day choice | PASS | Not specified in report |  | parking-request.allow-recurrence |  | apps/workplace/e2e/settings/parking-request/parking-request.allow-recurrence.spec.ts; status MD line 204
parking-request | parking.approver_groups | In PR #595 | 2 | [{"id":"e2e-approver-a","name":"E2E Approver A"},{"id":"e2e-approver-b","name":"E2E Approver B"}] [] | parking.approver_groups preselects the first option and renders every configured option in order parking.approver_groups empty hides the approver section | PASS | Not specified in report |  | parking-request.approver-groups |  | apps/workplace/e2e/settings/parking-request/parking-request.approver-groups.spec.ts; status MD line 205
parking-request | parking.auto_approved_groups | In PR #595 | 3 | ["e2e-approvers"] ["e2e-other-team"] [] | parking.auto_approved_groups matching user group hides the approver section parking.auto_approved_groups non-matching group keeps the approver section parking.auto_approved_groups empty keeps the approver section | PASS | Not specified in report |  | parking-request.auto-approved-groups |  | apps/workplace/e2e/settings/parking-request/parking-request.auto-approved-groups.spec.ts; status MD line 206
parking-request | parking.default_location_from_desk_booking | In PR #595 | 2 | false true | parking.default_location_from_desk_booking false selects the desk-booking building parking.default_location_from_desk_booking true selects the desk-booking building | PASS | Not specified in report |  | parking-request.default-location-from-desk-booking |  | apps/workplace/e2e/settings/parking-request/parking-request.default-location-from-desk-booking.spec.ts; status MD line 207
parking-request | parking.extra_space_restrictions | In PR #595 | 3 | [{"id":"e2e-standard-bay","name":"E2E Standard Bay"},{"id":"e2e-accessible-bay","name":"E2E Accessible Bay"}] [] | parking.extra_space_restrictions renders one toggle per option parking.extra_space_restrictions toggles independently and is reversible parking.extra_space_restrictions empty hides the extra list | PASS | Not specified in report |  | parking-request.extra-space-restrictions |  | apps/workplace/e2e/settings/parking-request/parking-request.extra-space-restrictions.spec.ts; status MD line 208
parking-request | parking.show_special_needs | In PR #595 | 2 | true false | parking.show_special_needs reveals the special needs details parking.show_special_needs false hides the special needs details | PASS | Not specified in report |  | parking-request.form-details |  | apps/workplace/e2e/settings/parking-request/parking-request.form-details.spec.ts; status MD line 209
parking-request | parking.request_submission_notes_html | In PR #595 | 2 | "" "<p>E2E submission note</p>" | parking.request_submission_notes_html renders the configured HTML parking.request_submission_notes_html empty renders no notes block | PASS | Not specified in report |  | parking-request.form-details |  | apps/workplace/e2e/settings/parking-request/parking-request.form-details.spec.ts; status MD line 210
parking-request | parking.can_book_for_anyone | In PR #595 | 2 | false true | parking.can_book_for_anyone true shows the request-space user search parking.can_book_for_anyone false hides the request-space user search | PASS | Not specified in report |  | parking-request.form-details |  | apps/workplace/e2e/settings/parking-request/parking-request.form-details.spec.ts; status MD line 211
parking-request | parking.hide_availability_counter | In PR #595 | 2 | false true | parking.hide_availability_counter false controls the location capacity counter parking.hide_availability_counter true controls the location capacity counter | PASS | Not specified in report |  | parking-request.hide-availability-counter |  | apps/workplace/e2e/settings/parking-request/parking-request.hide-availability-counter.spec.ts; status MD line 212
parking-request | parking.hide_custom_shift | In PR #595 | 3 | false true | parking.hide_custom_shift false controls the Custom Hours shift option parking.hide_custom_shift true controls the Custom Hours shift option parking.hide_custom_shift true with no presets forces the All Day window | PASS | Not specified in report |  | parking-request.hide-custom-shift |  | apps/workplace/e2e/settings/parking-request/parking-request.hide-custom-shift.spec.ts; status MD line 213
parking-request | parking.hidden_buildings | In PR #595 | 2 | [] ["e2e-request-parking-building-a"] | parking.hidden_buildings empty lists every building with parking levels parking.hidden_buildings removes the listed building from the options | PASS | Not specified in report |  | parking-request.location-preference |  | apps/workplace/e2e/settings/parking-request/parking-request.location-preference.spec.ts; status MD line 214
parking-request | parking.hide_prefer_toggle | In PR #595 | 2 | true false | parking.hide_prefer_toggle false shows the location preference toggle parking.hide_prefer_toggle true removes the location preference toggle | PASS | Not specified in report |  | parking-request.location-preference |  | apps/workplace/e2e/settings/parking-request/parking-request.location-preference.spec.ts; status MD line 215
parking-request | parking.request_shift_options | In PR #595 | 2 | [] Two presets: E2E Day Shift 480–1020; E2E Late Shift 600–1080 (minutes from midnight) | parking.request_shift_options supplies selectable presets parking.request_shift_options empty leaves only editable custom times | PASS | Not specified in report |  | parking-request.request-shift-options |  | apps/workplace/e2e/settings/parking-request/parking-request.request-shift-options.spec.ts; status MD line 216
parking-request | parking.request_space_restrictions | In PR #595 | 2 | [{"id":"e2e-standard-bay","name":"E2E Standard Bay"},{"id":"e2e-accessible-bay","name":"E2E Accessible Bay"}] [] | parking.request_space_restrictions renders a single-choice radio group parking.request_space_restrictions empty renders no radio group | PASS | Not specified in report |  | parking-request.request-space-restrictions |  | apps/workplace/e2e/settings/parking-request/parking-request.request-space-restrictions.spec.ts; status MD line 217
parking-request | parking.request_types | In PR #595 | 2 | [{"id":"standard","name":"E2E Commuter Request","description":"E2E commuter description","badge":"E2E Badge"},{"id":"e2e-night","name":"E2E Night Request"},{"id":"e2e-hidden","name":"E2E Group-only Request","groups":["e2e-no-such-group"]}] null | parking.request_types replaces the default request types parking.request_types unset shows the three default request types | PASS | Not specified in report |  | parking-request.request-types |  | apps/workplace/e2e/settings/parking-request/parking-request.request-types.spec.ts; status MD line 218
parking-request | parking.require_plate_number | In PR #595 | 2 | true false | parking.require_plate_number true controls the Registration required marker parking.require_plate_number false controls the Registration required marker | PASS | Not specified in report |  | parking-request.require-plate-number |  | apps/workplace/e2e/settings/parking-request/parking-request.require-plate-number.spec.ts; status MD line 219
parking-request | parking.require_space_restriction | In PR #595 | 2 | true false | parking.require_space_restriction true marks the restriction group required and invalid until a bay is chosen parking.require_space_restriction false marks the restriction group optional and valid without a choice | PASS | Not specified in report |  | parking-request.require-space-restriction |  | apps/workplace/e2e/settings/parking-request/parking-request.require-space-restriction.spec.ts; status MD line 220
parking-request | parking.vehicle_types | In PR #595 | 2 | [{"id":"e2e-ev","name":"E2E Electric"},{"id":"","name":"E2E Missing Id"},{"id":"e2e-moto","name":"E2E Motorbike"}] null | parking.vehicle_types replaces the vehicle choices parking.vehicle_types unset offers the five default vehicles | PASS | Not specified in report |  | parking-request.vehicle-types |  | apps/workplace/e2e/settings/parking-request/parking-request.vehicle-types.spec.ts; status MD line 221
room-booking | events.all_day_period | In PR #595 | 2 | {"start":9,"end":17} {"start":10,"end":16} | events.all_day_period 9-17 sets the unsaved all-day interval events.all_day_period 10-16 sets the unsaved all-day interval | PASS | Not specified in report |  | room-booking.all-day-period |  | apps/workplace/e2e/settings/room-booking/room-booking.all-day-period.spec.ts; status MD line 226
room-booking | events.allow_all_day | In PR #595 | 2 | false true | room settings: events.allow_all_day false gates the local all-day checkbox and timed controls room settings: events.allow_all_day true gates the local all-day checkbox and timed controls | PASS | Not specified in report |  | room-booking.allow-all-day |  | apps/workplace/e2e/settings/room-booking/room-booking.allow-all-day.spec.ts; status MD line 227
room-booking | events.allow_daily_allday_recurrence | In PR #595 | 2 | false true | events.allow_daily_allday_recurrence false controls form confirmation events.allow_daily_allday_recurrence true controls form confirmation | PASS | PPT-2861: Verified fixed | PPT-2861 | room-booking.allow-daily-allday-recurrence | PPT-2861 fixed on develop. The Daily→None repro is held locally (see below). | apps/workplace/e2e/settings/room-booking/room-booking.allow-daily-allday-recurrence.spec.ts; status MD line 228
room-booking | events.allow_externals | In PR #595 | 2 | false true | events.allow_externals false gates browser-fixture guest search results events.allow_externals true gates browser-fixture guest search results | PASS | Not specified in report |  | room-booking.allow-externals |  | apps/workplace/e2e/settings/room-booking/room-booking.allow-externals.spec.ts; status MD line 229
room-booking | events.allow_multiday | In PR #595 | 2 | false true | room settings: events.allow_multiday false switches duration to explicit end date and time room settings: events.allow_multiday true switches duration to explicit end date and time | PASS | Not specified in report |  | room-booking.allow-multiday |  | apps/workplace/e2e/settings/room-booking/room-booking.allow-multiday.spec.ts; status MD line 230
room-booking | events.allow_recurrence | In PR #595 | 2 | false true | room settings: events.allow_recurrence false gates recurrence for a timed meeting room settings: events.allow_recurrence true gates recurrence for a timed meeting | PASS | Not specified in report |  | room-booking.allow-recurrence |  | apps/workplace/e2e/settings/room-booking/room-booking.allow-recurrence.spec.ts; status MD line 232
room-booking | events.allowed_future_days | In PR #595 | 2 | 7 8 | room settings: events.allowed_future_days 7 allows boundary day and disables next day room settings: events.allowed_future_days 8 allows boundary day and disables next day | PASS | Not specified in report |  | room-booking.allowed-future-days |  | apps/workplace/e2e/settings/room-booking/room-booking.allowed-future-days.spec.ts; status MD line 233
room-booking | events.bookable_hours | In PR #595 | 3 | null {"start":6,"end":11} {"start":9,"end":17} | room settings: events.bookable_hours unset bounds tomorrow start options room settings: events.bookable_hours 6-11 bounds tomorrow start options room settings: events.bookable_hours 9-17 bounds tomorrow start options | PASS | Not specified in report |  | room-booking.bookable-hours |  | apps/workplace/e2e/settings/room-booking/room-booking.bookable-hours.spec.ts; status MD line 234
room-booking | events.booking_unavailable | In PR #595 | 2 | true false | room settings: booking_unavailable true opens the calendar-link dialog instead of the confirm screen room settings: with no_standalone and booking_unavailable false, Confirm opens the ordinary confirm screen | PASS | Not specified in report |  | room-booking.booking-unavailable |  | apps/workplace/e2e/settings/room-booking/room-booking.booking-unavailable.spec.ts; status MD line 235
room-booking | events.can_book_for_anyone | In PR #595 | 3 | false true | room settings: events.can_book_for_anyone false with can_book_for_others false sets the legacy host field room settings: events.can_book_for_anyone true with can_book_for_others false sets the legacy host field room settings: events.can_book_for_anyone true with can_book_for_others true sets the legacy host field | PASS | Not specified in report |  | room-booking.can-book-for-anyone | Legacy meeting form | apps/workplace/e2e/settings/room-booking/room-booking.can-book-for-anyone.spec.ts; status MD line 236
room-booking | events.can_book_for_others | In PR #595 | 2 | false true | room settings: events.can_book_for_others false gates the organiser control room settings: events.can_book_for_others true gates the organiser control | PASS | Not specified in report |  | room-booking.can-book-for-others |  | apps/workplace/e2e/settings/room-booking/room-booking.can-book-for-others.spec.ts; status MD line 237
room-booking | events.custom_duration_options | In PR #595 | 2 | [] [25,240] |  | PASS | Not specified in report |  | room-booking.custom-duration-options |  | apps/workplace/e2e/settings/room-booking/room-booking.custom-duration-options.spec.ts; status MD line 238
room-booking | events.duration_step | In PR #595 | 2 | 15 60 | events.duration_step 15 spaces the generated meeting durations events.duration_step 60 spaces the generated meeting durations | PASS | Not specified in report |  | room-booking.duration-step |  | apps/workplace/e2e/settings/room-booking/room-booking.duration-step.spec.ts; status MD line 239
room-booking | events.has_assets | In PR #595 | 2 | false true | events.has_assets false gates the unsaved asset field events.has_assets true gates the unsaved asset field | PASS | Not specified in report |  | room-booking.has-assets |  | apps/workplace/e2e/settings/room-booking/room-booking.has-assets.spec.ts; status MD line 240
room-booking | events.hide_attendees | In PR #595 | 2 | false true | events.hide_attendees false gates attendees while notes remain events.hide_attendees true gates attendees while notes remain | PASS | Not specified in report |  | room-booking.hide-attendees |  | apps/workplace/e2e/settings/room-booking/room-booking.hide-attendees.spec.ts; status MD line 241
room-booking | events.hide_features | In PR #595 | 2 | [] ["Prepared Projector"] |  | PASS | Not specified in report |  | room-booking.hide-features |  | apps/workplace/e2e/settings/room-booking/room-booking.hide-features.spec.ts; status MD line 242
room-booking | events.hide_nearby_desks | In PR #595 | 3 | false true | events.hide_nearby_desks success screen with desks feature, hide_nearby_desks false events.hide_nearby_desks success screen with desks feature, hide_nearby_desks true events.hide_nearby_desks success screen with no desks feature, hide_nearby_desks false (control) | PASS | Not specified in report |  | room-booking.hide-nearby-desks |  | apps/workplace/e2e/settings/room-booking/room-booking.hide-nearby-desks.spec.ts; status MD line 243
room-booking | events.hide_notes | In PR #595 | 2 | false true | events.hide_notes false gates notes while attendees remain events.hide_notes true gates notes while attendees remain | PASS | Not specified in report |  | room-booking.hide-notes |  | apps/workplace/e2e/settings/room-booking/room-booking.hide-notes.spec.ts; status MD line 244
room-booking | events.max_duration | In PR #595 | 2 | 120 240 | events.max_duration 120 caps the generated meeting durations events.max_duration 240 caps the generated meeting durations | PASS | Not specified in report |  | room-booking.max-duration |  | apps/workplace/e2e/settings/room-booking/room-booking.max-duration.spec.ts; status MD line 245
room-booking | events.min_duration | In PR #595 | 2 | 30 90 | events.min_duration 30 sets the lowest generated meeting duration events.min_duration 90 sets the lowest generated meeting duration | PASS | Not specified in report |  | room-booking.min-duration |  | apps/workplace/e2e/settings/room-booking/room-booking.min-duration.spec.ts; status MD line 246
room-booking | events.multiple_spaces | In PR #595 | 2 | false true | events.multiple_spaces false accumulates or replaces synthetic room choices events.multiple_spaces true accumulates or replaces synthetic room choices | PASS | Not specified in report |  | room-booking.multiple-spaces |  | apps/workplace/e2e/settings/room-booking/room-booking.multiple-spaces.spec.ts; status MD line 247
room-booking | events.no_standalone | In PR #595 | 1 | true | room settings: events.no_standalone true rejects a valid unsaved meeting without a room | PASS | Not specified in report |  | room-booking.no-standalone |  | apps/workplace/e2e/settings/room-booking/room-booking.no-standalone.spec.ts; status MD line 248
room-booking | events.strict_capacity_check | In PR #595 | 2 | false true | events.strict_capacity_check false gates the nonblocking capacity warning events.strict_capacity_check true gates the nonblocking capacity warning | PASS | Not specified in report |  | room-booking.strict-capacity-check |  | apps/workplace/e2e/settings/room-booking/room-booking.strict-capacity-check.spec.ts; status MD line 249
room-booking | events.use_bookings | In PR #595 | 2 | false true | events.use_bookings false selects the read-only availability backend events.use_bookings true selects the read-only availability backend | PASS | Not specified in report |  | room-booking.use-bookings |  | apps/workplace/e2e/settings/room-booking/room-booking.use-bookings.spec.ts; status MD line 250
room-booking | events.use_building_timezone | In PR #595 | 2 | false true | events.use_building_timezone false gates the duration secondary timezone events.use_building_timezone true gates the duration secondary timezone | PASS | Not specified in report |  | room-booking.use-building-timezone |  | apps/workplace/e2e/settings/room-booking/room-booking.use-building-timezone.spec.ts; status MD line 251
room-booking | events.allow_attendee_internal_or_external | In PR #595 | 2 | true false | events.allow_attendee_internal_or_external=true marks the attendee external in the saved event events.allow_attendee_internal_or_external=false hides the type block and saves no flags | PASS | Not specified in report |  | room-booking.allow-attendee-internal-or-external |  | apps/workplace/e2e/settings/room-booking/room-booking.allow-attendee-internal-or-external.spec.ts; status MD line 252
room-booking | events.allow_international | In PR #595 | 2 | true false | events.allow_international=true flags the attendee as international in the saved event events.allow_international=false hides the international block and saves no flags | PASS | Not specified in report |  | room-booking.allow-international |  | apps/workplace/e2e/settings/room-booking/room-booking.allow-international.spec.ts; status MD line 253
room-booking | events.breakdown | In PR #595 | 2 | 20 null | events.breakdown 20 sends a 20 minute breakdown time events.breakdown unset falls back to no breakdown time | PASS | Not specified in report |  | room-booking.breakdown | Added in 6be84e50c | apps/workplace/e2e/settings/room-booking/room-booking.breakdown.spec.ts; status MD line 254
room-booking | events.force_current_user_for_booking_rules | In PR #595 | 2 | true false | events.force_current_user_for_booking_rules=true applies the signed-in user's rules and permits the delegate booking events.force_current_user_for_booking_rules=false applies the delegate's rules and refuses the hidden room | PASS | Not specified in report |  | room-booking.force-current-user-for-booking-rules |  | apps/workplace/e2e/settings/room-booking/room-booking.force-current-user-for-booking-rules.spec.ts; status MD line 255
room-booking | events.force_host | In PR #595 | 2 | "forced-host@dev.place.tech" "" | events.force_host a forced address sends that host events.force_host '' keeps the signed-in user as host | PASS | Not specified in report |  | room-booking.force-host | Added in 6be84e50c | apps/workplace/e2e/settings/room-booking/room-booking.force-host.spec.ts; status MD line 256
room-booking | bookings.no_approval | In PR #595 | 2 | true false | bookings.no_approval true saves an approver's room booking as approved bookings.no_approval false leaves an approver's room booking tentative | PASS | Not specified in report |  | room-booking.no-approval | Added in 6be84e50c | apps/workplace/e2e/settings/room-booking/room-booking.no-approval.spec.ts; status MD line 257
room-booking | events.no_space_resource | In PR #595 | 2 | "e2e-no-space-resource-room-a" "e2e-no-space-resource-room-b" | events.no_space_resource selects synthetic fallback room 0 events.no_space_resource selects synthetic fallback room 1 | PASS | Not specified in report |  | room-booking.no-space-resource |  | apps/workplace/e2e/settings/room-booking/room-booking.no-space-resource.spec.ts; status MD line 258
room-booking | events.room_as_host | In PR #595 | 2 | true | events.room_as_host true sends the first room as host events.room_as_host true with force_host set sends the forced host (force_host wins) | PASS | Not specified in report |  | room-booking.room-as-host | Added in 6be84e50c. One dev-server hiccup in the full run; 6/6 on repeat. | apps/workplace/e2e/settings/room-booking/room-booking.room-as-host.spec.ts; status MD line 259
room-booking | events.setup | In PR #595 | 2 | 15 null | events.setup 15 sends a 15 minute setup time events.setup unset falls back to no setup time | PASS | Not specified in report |  | room-booking.setup | Added in 6be84e50c | apps/workplace/e2e/settings/room-booking/room-booking.setup.spec.ts; status MD line 260
room-booking | events.allow_multiple_spaces (legacy alias) | In PR #595 | 1 | true | events.allow_multiple_spaces legacy alias enables multi-room selection | PASS | Not specified in report |  | room-booking.allow-multiple-spaces-legacy |  | apps/workplace/e2e/settings/room-booking/room-booking.allow-multiple-spaces-legacy.spec.ts; status MD line 261
room-booking | events.catering_notes_required | In PR #595 | 2 | true false | events.catering_notes_required true rejects a catering order without notes events.catering_notes_required false accepts a catering order without notes | PASS | Not specified in report |  | room-booking.catering-notes-required |  | apps/workplace/e2e/settings/room-booking/room-booking.catering-notes-required.spec.ts; status MD line 262
room-booking | catering_provider | In PR #595 | 2 | "Beta" "" | catering_provider 'Beta' sets the caterers the menu offers catering_provider unset sets the caterers the menu offers | PASS | Not specified in report |  | room-booking.catering-provider |  | apps/workplace/e2e/settings/room-booking/room-booking.catering-provider.spec.ts; status MD line 263
room-booking | events.default_duration | In PR #595 | 2 | 45 minutes Unset / effective null → 60-minute fallback | events.default_duration 45 applies 45 minutes when leaving a date-shifted all-day meeting events.default_duration fallback applies 60 minutes when leaving a date-shifted all-day meeting | PASS | Not specified in report |  | room-booking.default-duration |  | apps/workplace/e2e/settings/room-booking/room-booking.default-duration.spec.ts; status MD line 264
schedule | schedule.event_sources | In PR #595 | 2 | ["api"] ["driver"] | schedule.event_sources api selects the schedule event source schedule.event_sources driver selects the schedule event source | PASS | Not specified in report |  | schedule.event-sources |  | apps/workplace/e2e/settings/schedule/schedule.event-sources.spec.ts; status MD line 269
schedule | visitors.allow_editing | In PR #595 | 2 | true false | visitors.allow_editing true gates Edit for a synthetic owned visitor booking visitors.allow_editing false gates Edit for a synthetic owned visitor booking | PASS | Not specified in report |  | schedule.visitors-allow-editing |  | apps/workplace/e2e/settings/schedule/schedule.visitors-allow-editing.spec.ts; status MD line 270
schedule | auto_release.time_after | In PR #595 | 2 | 10 60 | auto_release.time_after 10 skips a booking that started 20 minutes ago auto_release.time_after 60 prompts for a booking that started 20 minutes ago | PASS | Not specified in report |  | schedule.auto-release |  | apps/workplace/e2e/settings/schedule/schedule.auto-release.spec.ts; status MD line 271
schedule | auto_release.time_before | In PR #595 | 2 | 0 60 | auto_release.time_before 0 skips a booking that starts in 30 minutes auto_release.time_before 60 prompts for a booking that starts in 30 minutes | PASS | Not specified in report |  | schedule.auto-release |  | apps/workplace/e2e/settings/schedule/schedule.auto-release.spec.ts; status MD line 272
schedule | auto_release.all_day_start | In PR #595 | 2 | Current UTC hour Two hours away from current UTC hour | auto_release.all_day_start at the current hour prompts for an all-day booking auto_release.all_day_start two hours away skips an all-day booking | PASS | Not specified in report |  | schedule.auto-release |  | apps/workplace/e2e/settings/schedule/schedule.auto-release.spec.ts; status MD line 273
schedule | auto_release.resources | In PR #595 | 2 | ["desk"] ["parking"] | auto_release.resources ['desk'] queries desk bookings and prompts auto_release.resources ['parking'] queries only parking and does not prompt | PASS | Not specified in report |  | schedule.auto-release |  | apps/workplace/e2e/settings/schedule/schedule.auto-release.spec.ts; status MD line 274
schedule | schedule.use_driver | In PR #595 | 2 | true | schedule.use_driver true selects the driver event source schedule.use_driver true with use_websocket true selects the driver event source | PASS | Not specified in report |  | schedule.use-driver |  | apps/workplace/e2e/settings/schedule/schedule.use-driver.spec.ts; status MD line 275
schedule | schedule.use_websocket | In PR #595 | 2 | true false | schedule.use_websocket true selects the ws event source schedule.use_websocket false selects the api event source | PASS | Not specified in report |  | schedule.use-websocket |  | apps/workplace/e2e/settings/schedule/schedule.use-websocket.spec.ts; status MD line 276
visitor-invite | visitors.allow_all_day | In PR #595 | 2 | false true | visitors.allow_all_day false gates the unsaved visitor all-day control visitors.allow_all_day true gates the unsaved visitor all-day control | PASS | Not specified in report |  | visitor-invite.allow-all-day |  | apps/workplace/e2e/settings/visitor-invite/visitor-invite.allow-all-day.spec.ts; status MD line 281
visitor-invite | visitors.allow_international | In PR #595 | 2 | false true | visitors.allow_international false offers the per-visitor international flag visitors.allow_international true offers the per-visitor international flag | PASS | Not specified in report |  | visitor-invite.allow-international | Docs and schema wording corrected earlier in the PR | apps/workplace/e2e/settings/visitor-invite/visitor-invite.allow-international.spec.ts; status MD line 282
visitor-invite | visitors.allow_pass_number | In PR #595 | 2 | false true | visitors.allow_pass_number false shows the visitor pass number field visitors.allow_pass_number true shows the visitor pass number field | PASS | Not specified in report |  | visitor-invite.allow-pass-number |  | apps/workplace/e2e/settings/visitor-invite/visitor-invite.allow-pass-number.spec.ts; status MD line 283
visitor-invite | visitors.allow_visitor_internal_or_external | In PR #595 | 2 | false true | visitors.allow_visitor_internal_or_external false offers the visitor type choice visitors.allow_visitor_internal_or_external true offers the visitor type choice | PASS | Not specified in report |  | visitor-invite.allow-visitor-internal-or-external |  | apps/workplace/e2e/settings/visitor-invite/visitor-invite.allow-visitor-internal-or-external.spec.ts; status MD line 284
visitor-invite | visitors.bookable_hours | In PR #595 | 1 | {"start":10,"end":16} | visitors.bookable_hours limits the start times to the configured window | PASS | Not specified in report |  | visitor-invite.bookable-hours |  | apps/workplace/e2e/settings/visitor-invite/visitor-invite.bookable-hours.spec.ts; status MD line 285
visitor-invite | visitors.use_building_timezone | In PR #595 | 2 | false true | visitors.use_building_timezone false leaves the time field in the browser zone visitors.use_building_timezone true adds the building timezone label | PASS | Not specified in report |  | visitor-invite.building-timezone |  | apps/workplace/e2e/settings/visitor-invite/visitor-invite.building-timezone.spec.ts; status MD line 286
visitor-invite | visitors.can_book_for_anyone | In PR #595 | 2 | false true | visitors.can_book_for_anyone false selects the visitor host-search branch visitors.can_book_for_anyone true selects the visitor host-search branch | PASS | Not specified in report |  | visitor-invite.can-book-for-anyone |  | apps/workplace/e2e/settings/visitor-invite/visitor-invite.can-book-for-anyone.spec.ts; status MD line 287
visitor-invite | visitors.can_book_for_others | In PR #595 | 2 | false true | visitors.can_book_for_others false gates the visitor host selector visitors.can_book_for_others true gates the visitor host selector | PASS | Not specified in report |  | visitor-invite.can-book-for-others |  | apps/workplace/e2e/settings/visitor-invite/visitor-invite.can-book-for-others.spec.ts; status MD line 288
visitor-invite | visitors.min_duration | In PR #595 | 1 | 60 30 45 | visitors.min_duration bounds the duration menu and removes shorter options | PASS | Not specified in report |  | visitor-invite.duration-options |  | apps/workplace/e2e/settings/visitor-invite/visitor-invite.duration-options.spec.ts; status MD line 289
visitor-invite | visitors.max_duration | In PR #595 | 1 | 180 120 225 | visitors.max_duration removes longer options from the duration menu | PASS | Not specified in report |  | visitor-invite.duration-options |  | apps/workplace/e2e/settings/visitor-invite/visitor-invite.duration-options.spec.ts; status MD line 290
visitor-invite | visitors.duration_step | In PR #595 | 1 | 30 45 | visitors.duration_step changes the spacing of duration options | PASS | Not specified in report |  | visitor-invite.duration-options |  | apps/workplace/e2e/settings/visitor-invite/visitor-invite.duration-options.spec.ts; status MD line 291
visitor-invite | visitors.custom_duration_options | In PR #595 | 1 | null [45,200] | visitors.custom_duration_options adds exact values outside the generated step | PASS | Not specified in report |  | visitor-invite.duration-options |  | apps/workplace/e2e/settings/visitor-invite/visitor-invite.duration-options.spec.ts; status MD line 292
visitor-invite | bookings.multiple_visitors | In PR #595 | 2 | false true | bookings.multiple_visitors false selects the legacy visitor fields bookings.multiple_visitors true selects the legacy visitor fields | PASS | Not specified in report |  | visitor-invite.multiple-visitors | Legacy visitor form | apps/workplace/e2e/settings/visitor-invite/visitor-invite.multiple-visitors.spec.ts; status MD line 293
visitor-invite | visitors.reason_required | In PR #595 | 2 | false true | visitors.reason_required false changes the unsent reason validation visitors.reason_required true changes the unsent reason validation | PASS | Not specified in report |  | visitor-invite.reason-required |  | apps/workplace/e2e/settings/visitor-invite/visitor-invite.reason-required.spec.ts; status MD line 294
visitor-invite | visitors.show_calendar_links | In PR #595 | 2 | false true | visitors.show_calendar_links false gates links for browser-only success state visitors.show_calendar_links true gates links for browser-only success state | PASS | Not specified in report |  | visitor-invite.show-calendar-links |  | apps/workplace/e2e/settings/visitor-invite/visitor-invite.show-calendar-links.spec.ts; status MD line 295
visitor-invite | bookings.all_day_period | In PR #595 | 2 | {"start":9,"end":17} {"start":8,"end":12} | bookings.all_day_period 9-17 sets the unsaved all-day visitor window bookings.all_day_period 8-12 sets the unsaved all-day visitor window | PASS | Not specified in report |  | visitor-invite.all-day-period |  | apps/workplace/e2e/settings/visitor-invite/visitor-invite.all-day-period.spec.ts; status MD line 296
parking-booking | parking.hide_selected_space | Held local | 4 | true / false; card and details pop-up | parking.hide_selected_space true controls the space name on the card parking.hide_selected_space false controls the space name on the card parking.hide_selected_space true controls the space name in the booking details parking.hide_selected_space false controls the space name in the booking details | Card true case fails (fix not on branch) | 4/4 PASS | PPT-2863 / PPT-2858 verified | parking-booking.hide-selected-space | Add to the PR once the fix reaches the branch | apps/workplace/e2e/settings/parking-booking/parking-booking.hide-selected-space.spec.ts; status MD line 302
explore | explore.hide_device_fields | Held local | 2 | [] / ['mac','manufacturer']; real device hover | explore.hide_device_fields=[] controls the device tooltip rows explore.hide_device_fields=['mac','manufacturer'] controls the device tooltip rows | Fails (tooltip can't open) | Tooltip rows pass; fails at the owner lookup | PPT-2865 verified; PPT-2868 open | explore.hide-device-fields | Add after PPT-2868 is fixed | apps/workplace/e2e/settings/explore/explore.hide-device-fields.spec.ts; status MD line 303
room-booking | events.allow_daily_allday_recurrence | Held local | 1 | false; All Day + Daily → None; standalone confirmation cancelled | events.allow_daily_allday_recurrence false: Daily then None does not block confirmation | Fails (fix not on branch) | PASS | PPT-2861 verified | room-booking.allow-daily-allday-recurrence (local addition) | Add to the PR once the fix reaches the branch | apps/workplace/e2e/settings/room-booking/room-booking.allow-daily-allday-recurrence.spec.ts; status MD line 304
lockers | – (product check, not a setting) | Held product check | 1 | N/A — picker load with map view | locker picker map view logs no error while its lockers load | – | Fails: TypeError reproduced | PPT-2870 open | lockers.picker-loading | Keep as a regression check after the fix | apps/workplace/e2e/settings/lockers/lockers.picker-loading.spec.ts; status MD line 305